## G Y R Status Definition
Advanced Product and Quality Planning (APQP) The Modine APQP process ensures the supplier utilizes adequate planning to support the development and launch of parts and materials. Modine requires suppliers to use the Automotive Industry Action Group (AIAG)’s "Advanced Product Quality Planning and Control Plan” discipline or an equivalent supplier-developed APQP process (approved by Modine SQE or Plant Quality Management). Modine has developed an APQP Supplier reporting template that may be used for reporting the supplier’s status to Modine. Modine expects that Suppliers will enforce the usage of APQP disciplines with their sub suppliers and will provide Modine visibility to their supporting supply chain and the supply chain APQP status.
G Y R Status Rating Criteria
G Y R Status | Enter G, Y or R, as appropriate. GYR assesses whether the expectations of the deliverable will be completed in time to meet the project need date.
Red (High Risk): R ratings are given prior to the Project Need Date to indicate a deliverable will not meet the Project Need Date or quality expectations. R signifies the project is at risk and needs immediate management attention. Any deliverable not completed by its Project Need Date must be carry an R rating until the deliverable is completed.
Yellow (Low Risk): Y ratings are given prior to the Project Need Date to indicate an deliverable may not meet the Program Need Date or quality expectations. To be considered Y, a recovery plan must be in place for the deliverable. Y ratings indicate the need for project management attention. A Y rating can only be given to an deliverable prior to the Project Need Date.
Green (No Risk): G ratings are given before the Project Need Date to indicate the deliverable will meet the Project Need Date and will meet all quality expectations. G ratings given on the Project Need Date indicate the deliverable is complete and meets all quality expectations listed on the "Required Evidence" sheet and AIAG APQP Manual for that deliverable. No risk to other deliverables is apparent.
NOTE: The supplier must have a documented Recovery Plan for any deliverable rated "Yellow" or "Red".

## APQP Status Reporting Template
Date:
Supplier | [9 empty] | Project
Location | [9 empty] | Modine Contact
Supplier Code | [9 empty] | Part No.
Risk Assessment | [9 empty] | Part Name
New : |  | Site |  | Technology |  |  | Process |  |  | Change Level/Date
|  | Other Risks | [7 empty] | User Plant(s)
Core Team Members |  |  |  | Company/Title | [5 empty] | Phone/Fax/E-Mail
| Build Level |  | Material |  |  |  | Quantity |  |  | No. Concurred
|  |  | Required Date | [6 empty] | SRCs | Majors
[5 empty] | Modine APQP Reference Only | G |  | Project | Supplier | Actual | Supplier | Modine
APQP Deliverable | [5 empty] | Y |  | Need | Timing | Closure | Lead Resp | Acceptance | Remarks or
[6 empty] | R |  | Date | Date | Date | Initials | Complete | Assistance Required
AIAG APQP Phase 2 - Product Design and Development
1. Project Timeline (Synchronized w/Production Time Plan) |  |  |  |  | 2030
2. Customer Inputs / Requirements |  |  |  |  | 2030
3. Warranty & Quality Mitigation Plan |  |  |  |  | 2030
4. Customer Specific Requirements |  |  |  |  | 2050
5. Design FMEA |  |  |  |  | 2080
6. Preliminary Bill of Materials (BOM) |  |  |  |  | 2090
7. Prototype Control Plans |  |  |  |  | 2110
8. Prototype Builds |  |  |  |  | 2110
9. Design Verification Plan & Report (DVP&R) |  |  |  |  | 2120
10. Design / Process Review |  |  |  |  | 2130
11. Team Feasibility Commitment |  |  |  |  | 2130
12. APQP Status Sub-Supplier |  |  |  |  | 2130
13. Production Drawing & Specifications |  |  |  |  | 2220
14. Subcontractor Purchase Orders (Customer Tooling PO Rec.) |  |  |  |  | 2250
15. Facilities, Equipment, Tools and Gages - New equip., tooling and facilities requirements. - gage/test equipment requirements - special product/process characteristics |  |  |  |  | 2260
AIAG APQP Phase 3 - Process Design and Development
16. Product/Process and Quality System Review |  |  |  |  | 3030
17. Manufacturing Process Flow Chart |  |  |  |  | 3040
18. Process FMEA |  |  |  |  | 3100
19. Pre-Launch Control Plan - heat treament assessment (if applicable) - product identification & traceability plan |  |  |  |  | 3110
20. Process Work Instructions - tooling and machine maintenance plan |  |  |  |  | 3120
21. Measurement Systems Evaluation - measurement system analysis plan - preliminary process capability study plan |  |  |  |  | 3130
22. Packaging Specifications & Approvals |  |  |  |  | 3160
23. Manufacturing Team Training |  |  |  |  | 3170
AIAG APQP Phase 4 - Product and Process Validation
24. Subcontractor PPAP Approval |  |  |  |  | 4005
25. Production Control Plan - operator work instructions |  |  |  |  | 4008
26. Production Reasiness Review (PRR) |  |  |  |  | 4009
27. Production Trial Run (PTR) - Run at Rate for Capacity - Measurement System Evaluation - Gage R & R |  |  |  |  | 4010
28. Process Capability Studies |  |  |  |  | 4030
29. Production Validation Plan & Report (PVP&R) |  |  |  |  | 4090
30. Production Part Approval (PPAP) |  |  |  |  | 4110
AIAG APQP Phase 5 - Feedback, Assessment and Corrective Action
31. Initial Production Shipment |  |  |  |  | 5005
32. Production Ramp-up Plan |  |  |  |  | 5005
33. Full Production Date |  |  |  |  | 5005
34. Conduct Lessons Learned |  |  |  |  | 5005
Initial Commitment Approval:
|  |  |  | Supplier Project Manager | [6 empty] | Modine Project Manager
COMMENTS:
2130
Advanced Product Quality Planning Supplier Status Report - Basic Supplier Form

## Required Evidence
Note: This document is intended to provide guideance to the supplier regarding the type of evindence required to complete each of the APQP process steps.
Modine APQP - Critical Supplier Status Report Evidence and Responsibility Matrix
APQP DELIVERABLE | DOCUMENTED EVIDENCE | RESPONSIBILITY GUIDE CFT = Cross Functional Team
0. Approved Modine P.O. / Contract | Supplier P.O. Acknowledgement mailed back to Modine (Contract Award Date to be shown in the Project Schedule). | Sales & Project Manager
AIAG APQP Phase 2 - Product Design and Development
1. Project Timeline (Synchronized w/Production Time Plan) | Complete project timeline defining, at a minimum, the Tasks associated with the APQP Deliverables in this Status Report. Supplier Project Schedule must meet Modine's defined milestones. | Project Manager & CFT
2. Customer Inputs / Requirements | Complete Customer requirements including Design Criteria, Program Requirements, Supplier Manual Requirements. | Sales
3. Warranty & Quality Mitigation Plan | Gap Analysis of Past Warranty & Quality Issues, Mitigation Action Plan (or Failure Mode Analsis - FMA). | Product Engineering & Quality
4. Customer Specific Requirements | Customer specific requirements including Risk Characteristics <RC> and Major Characteristics <MC>
5. Design FMEA | Production Level DFMEA with Pareto of High Severity/High RPN Items and Completed Recommended Actions | Product Engineering & CFT
6. Preliminary Bill of Materials (BOM) | Preliminary Engineering or Manufacuring Bill of Materials | Product Engineering
7. Prototype Control Plans | Approved Prototype Control Plans | Quality & Product Engineering
8. Prototype Builds | Prototype Part Delivery and Required Part Documentation per Prototype Purchase Order (Project Schedule to include Prototype Part Design, Tooling, Manufacture and Assembly). | Project Manager & CFT
9. Design Verification Plan & Report (DVP&R) | Approved DVP&R including Test Data and Closure of Design Review Issues | Product Engineering & CFT
10. Design / Process Review | Final Design Review, prior to Production tooling launch with Minutes and Open Issues | Project Manager & CFT
11. Team Feasibility Commitment | Completed Team Feasibility Commitment for Production Design (per AIAG APQP Manual) | Project Manager & CFT
12. APQP Status Sub-Supplier | Initial Supplier APQP Status Report Matrix with Open Issues for all Critical to Program Subcontractors. Supplier APQP Status Reports Samples with Planned Timing Dates, Lead Responsibility and Program Need Dates. | Project Manager & CFT
13. Production Drawing & Specifications | Released Production Drawings and Specifications with Special (SRC, Major, etc.) Characteristics Identified | Product Engineering & CFT
14. Subcontractor Purchase Orders (Customer Tooling PO Rec.) | P.O's issued to Subcontractors with commitment dates for samples / PPAP | Procurement
15. Facilities, Equipment, Tools and Gages - New equip., tooling and facilities requirements. - gage/test equipment requirements - special product/process characteristics | Facilities, Equipment, Tools and Gages complete and available (Project Schedule to include Facilities, Production Equipment/Tools and Gage Design, Fabrication, Qualification and Installation). | Manufacturing Engineering & Quality
AIAG APQP Phase 3 - Process Design and Development
16. Product/Process and Quality System Review | Final Process Design Review, prior to Production tooling launch with Minutes and Open Issues | Project Manager & CFT
17. Manufacturing Process Flow Chart | Production Level Manufacturing Process Flow Chart | Manufacturing Engineering
18. Process FMEA | Production Level PFMEA with Pareto of High Severity/High RPN Items and Completed Recommended Actions | Manufacturing Engineering & CFT
19. Pre-Launch Control Plan - heat treament assessment (if applicable) - product identification & traceability plan | Approved Pre-Launch Control Plan | Quality & Manufacturing Engineering
20. Process Work Instructions - tooling and machine maintenance plan | Copy of Preventive maintenance plan for tooling and equipment | Manufacturing Engineering
21. Measurement Systems Evaluation - measurement system analysis plan - preliminary process capability study plan | Matrix of GR&R, Calibration Results (including Bias, Linearity and Stability) and Approval Date with Data Analysis Samples | Quality & Manufacturing Engineering
22. Packaging Specifications & Approvals | Packaging & Labeling Specifications and Evaluation Approvals with contingency packaging plans | Materials & Logistics
23. Manufacturing Team Training | Manufacturing Team (Operators, Product Auditors, etc.) Training Records | Manufacturing & Human Resources
AIAG APQP Phase 4 - Product and Process Validation
24. Subcontractor PPAP Approval | Completed Critical Supplier APQP Status Report Matrix with Closed Issues and Approved PPAP for Subcontractor Materials/Parts | Project Manager & Quality
25. Production Control Plan - operator work instructions | Approved Production Control Plan Matrix of Work Instructions with Completion Status and Instruction Samples | Quality Manufacturing Engineering
26. Production Readiness Review (PRR) | Production Readiness Audit Results, Process Sign-Off Form or equivalent and Open Issues Matrix | Quality & Manufacturing
27. Production Trial Run - Run at Rate for Capacity - Measurement System Evaluation - Gage R & R | Production Readiness Audit Results, Process Sign-Off Form or equivalent, Run at Rate Data and Open Issues Matrix | Quality & Manufacturing
28. Process Capability Studies | Matrix of Capability Results and Equipment / Tooling Approval Date with Data Analysis Samples | Quality & Manufacturing
29. Production Validation Plan & Report (PVP&R) | Approved PVP&R including Test Data | Product Engineering & CFT
30. Production Part Approval (PPAP) | Approved PPAP Package (including Modine Approvals, if not approved by the Modine plant to be self-certifying) | Quality
AIAG APQP Phase 5 - Feedback, Assessment and Corrective Action
31. Initial Production Shipment | Initial Production Shipment completed including trail of Modine Releases, EDI/e-Kanban (if required), ASNs (if required) and Complete Shipping Documentation. | Materials & Logistics
32. Production Ramp-up Plan | Time period and rates of ramp-up to full production volumes | Materials & Logistics
33. Full Production Date | Production volumes achieved, all issues closed and project targets met | Project Manager & CFT
34. Conduct Lessons Learned |  | Project Manager & CFT
NOTE: A documented supplier Recovery Plan is required for any deliverable rated "Yellow" or "Red".